Collaboration Compact

Collaborators: Anna Boser, Annette Hilton

Project: Deep learning for historical data digitization

Project major milestones

- Undergraduate hire for machine learning

- Literature review completed

- Machine/deep learning algorithms completed

- Digitization of documents

  - Data repository of digitized data (uncleaned)

  - Compilation and cleaning of data for analysis

- Analysis of water data in SB County (case-study)

- Expansion of case-study to California (possibly?)

- Present at AGU Fall Meeting with students

- Draft manuscript

- Submit manuscript

Expected timeline of project

Timeline of this project is located in this doc and will be updated throughout: Project Timeline Chapter 3_Anna_Annette

General timeline

Spring Quarter '24:

- Hire undergraduate, start machine/deep learning algorithm development

- Luma (other undergraduate–Schmidt) possibly start (literature review)

Summer Quarter '24:

- Machine/deep learning algorithm development

- Testing digitization techniques and algorithms

- Finalize algorithms, data digitization

- Luma literature review work, other

Fall Quarter '24:

- Database housing, data cleaning

- Data analysis SB County

- Data analysis CA

- Prepare for AGU

Winter Quarter '25:

- Finalize analyses (expand to CA)

- Draft manuscript

Spring Quarter '25:

- Manuscript submission

- Finalize databases and repositories for publication

Job duties

Annette

I am broadly responsible for this entire project, as it is a chapter of my dissertation. I hold the project vision, design, and scope (in consultation with my committee).

Specifically, I am responsible for:

- Funding for the hire of undergraduate students (Coastal Fund, Schmidt Fellowship), including the management and payroll/approval of those funds

- Primary mentorship of the Schmidt undergraduate student, Luma Braconi Lazarini

- Co-mentorship of the Coastal Fund undergraduate student (algorithm development)

- Consulting with my co-advisors to scope and incorporate feedback into the project throughout

- Consulting with committee member Kelly Caylor (with Anna) to scope and incorporate feedback into the project throughout

- Communicating any changes in scope, timeline, focus to Anna and undergraduate students in a timely manner (I will always communicate to Anna first)

- Design of data analysis question for water in Santa Barbara County, application example of historical data

- Completion of data analysis case-study (SB County, CA), with possible assistance from collaborators (Anna, undergraduates)

- The management of any resulting data repositories or datasets

- Primary writer of manuscript, I will draft the initial manuscript and send to co-authors for edits and input

- Corresponding author on resulting publication, including primary responsibility for peer-review edits and process

Intellectual property:

- Co-owner/developer of algorithms

- Primary owner of resulting datasets and their management

- Primary/first author on publications, including AGU poster and peer-reviewed paper

Anna

- Primarily responsible for ensuring the mentorship of the Coastal Fund student and development of the OCR algorithm

- Jointly responsible for coming up with a timeline for the undergraduate’s progress

- Responsible for consulting with Kelly on the project

- Editor and collaborator on manuscript

- Collaborator on data analysis case-study

- Co-author on any resulting publications, including reviewing and editing any manuscripts and aiding with revisions.

Mentorship of undergraduate

Time available for individual mentoring

- Anna is available for up to 1 hour/week during the school year and up to 2 hours/week in the summer, but expects that ≤ half that much time would be necessary once we’re settled in (from prior experience). In general, I allow more meetings scheduled and for longer than I expect will be needed and let students delete them/cut them short as needed to ensure they have as much time as they need for help.

Time available for group mentoring

- Anna is available for up to 1 hour/week during the school year and up to 2 hours/week in the summer, but expects that ≤ half that much time would be necessary once we’re settled in (from prior experience)

Emails

- I am available over email and respond within 48 business hours. I usually have a slack that I use to communicate with undergrads over shorter time frames – I find this very helpful for small fixes and updates that don’t require a full meeting.

Meetings

Authorship and publications

Annette is first author and Anna is expected to be second, followed by undergrads and potentially Kelly Caylor depending on his contributions to the project.

General time allocations, constraints

Anna

I generally expect to spend about 1-3 hours a week on this project, depending on what’s needed and what stage of the project we’re on. I expect to spend more time in the summer than during the school year because mentoring responsibilities will go up. Constraints are that I apparently travel an extreme amount, most notably I expect to be in Niger over summer ~late July - August. I will however be available to work on this project/mentor students remotely.

Funding (AGU, publication)

AGU fall meeting conference funding

- Anna expects to find funding for AGU elsewhere but in the event I have trouble may ask Annette if she would be ok with sharing a room

Publication funding

- The library is expected to cover the publication costs (between Anna and Annette we are 4 for 4)